## Activity_Plan
# | 1. Cathegory | 2. Description | 3. Responsible entity (Lead applicant / Co-applicant / Other | 4. Partners | 5. Timeframe | 6. Human resources needed | 7. Planned costs | 8. Real costs | 9. Assumptions | 10. Links with other actions | 11. Status
| Strategic Goal (impact) | To support revitalization of Charentsavan and its sustainable economic growth through industrial heritage preservation and popularization, thereby unlocking local artistic potential | Municipality of Charentsavan, Foundation of cultural development of Charentsavan/to be established / | Local organizations/local CSOs, businesses, local creative artists/ | June 2022- December 2026 |  | 304350 | 0
O1 | Operative Goal (outcome) | A foundation of cultural development of Charentsavan is properly established and functioning mechanisms set to be the leader of cultural development in the area | Municipality of Charentsavan | Local creative artists and organizations |  |  | 73350 | 0
O1.1 | Action (output) | Following an inclusive discussion process, the structure of the future foundation and its founding documentation are ready | Municipality of Charentsavan | Local creative artists , local CSOs, community-based organizations |  |  | 73350 | 0
A1.1.1 | Activity | To develop the draft charter of future foundation | Charetsavan municipality and co-founders | Local creative artists , local CSOs, community-based organizations |  | n/a | 0 | 0 |  | A2.2.3 | Planned
A1.1.2 | Activity | To discuss the charter with stakeholders to decide the participation of each of them as founders | Charetsavan municipality and co-founders | Local creative artists , local CSOs, community-based organizations |  | n/a | 0 | 0 |  |  | Planned
A1.1.3 | Activity | Registration of the foundation is implemented | Charetsavan municipality and co-founders | Local creative artists , local CSOs, community-based organizations |  | n/a | 0 | 0 |  | A1.1.2, A1.1.1 | Planned
A1.1.4 | Activity | To organize the hiring process of the manager of the Foundation and to decide on organizational chart | Charetsavan municipality and co-founders | Local creative artists , local CSOs, community-based organizations |  | project manager, event and PR manager, officer | 65000 | 0 |  | A1.1.4 | Planned
A1.1.5 | Activity | To organize a proper office space for the foundation | Charetsavan municipality | n/a |  | n/a | 0 | 0 |  | A1.1.3 | Planned
A1.1.6 | Activity | To procure equipment and office furniture for the staff of the foundation/for 3 people/ | Charetsavan municipality | n/a |  | n/a | 5350 | 0 |  | A1.1.4 | Planned
A1.1.7 | Activity | To outsource baseline assessment | Charetsavan municipality | n/a | outsourced company | n/a | 3000 | 0 |  |  | Planned
O1.2 | Action | The foundation is established and operating, with a strong aim to bring into life the cultural strategy through various projects and in cooperation with different stakeholders/partners | Foundation of cultural development of Charentsavan | Local creative artists and organizations |  |  | 0 | 0
A1.2.1 | Activity | Adoption of the current CDS into an action plan by the Foundation | Foundation of cultural development of Charentsavan | n/a |  | n/a | 0 | 0 |  |  | Planned
A1.2.2 | Activity | To organize marz-level and national stakeholders meeting to inform and disseminate strategy and action plan | Municipality of Charentsavan, Foundation of cultural development of Charentsavan | Local creative artists and organizations, marz administration |  | n/a | 0 | 0 |  |  | Planned
A1.2.3 | Activity | To implement available projects and opportunities mapping for the available cultural interchange and development actions by other national or international organizations that are in line with the CDS | Foundation of cultural development of Charentsavan | Other partners to be identified |  | n/a | 0 | 0 |  |  | Planned
A1.2.4 | Activity | The Foundation is implementing the CDS and its action plan | Foundation of cultural development of Charentsavan | All the partners in respective actions |  | n/a | 0 | 0 |  |  | Planned
A1.2.5 | Activity | The Foundation provides reports and organizes meetings to inform and present the operations | Foundation of cultural development of Charentsavan | n/a |  | n/a | 0 | 0 |  |  | Planned
O2 | Operative Goal (outcome) | Charentsavan industrial and cultural heritage in- dept research is conducted, the assets’ preservation and exhibition are properly managed | Foundation of cultural development of Charentsavan | Partner and outsourced organizations from Armenia |  |  | 181100 | 0
O2.1 | Action (output) | Industrial and cultural heritage objects are properly mapped, and action plans on them are in place | Foundation of cultural development of Charentsavan, Municipality of Charentsavan | National partners for cultural objects of national importance, Marz administartion |  |  | 12000 | 0
A2.1.1 | Activity | To make a list of intangible cultural heritage objects and collect preliminary data | Foundation of cultural development of Charentsavan, Municipality of Charentsavan |  |  | n/a | 0 | 0 |  | A2.1.2 | Planned
A2.1.2 | Activity | To enhance the list and description of around 60 cultural heritage objects in the area | Foundation of cultural development of Charentsavan, Municipality of Charentsavan |  |  | n/a | 0 | 0 |  | A2.1.1 | Planned
A2.1.3 | Activity | To conduct a research of cultural heritage objects, their current condition, location and mapping , provide conclusions for reconstruction/restoration needs and to collect stories of the most important artifacts to be included on the main exhibition of the future museum | Municipality of Charentsavan | volunteers, local organizations, outsourced company |  | n/a | 12000 | 0 |  | A2.1.1, A2.1.2 | Planned
A2.1.4 | Activity | In-dept research results are shared with stakeholders/ locally and nationally/ to engage into action | Foundation of cultural development of Charentsavan | Foundation of cultural development of Charentsavan |  | n/a | 0 | 0 |  |  | Planned
A2.1.5 | Activity | To develop 3-year cultural development plan of Charentsavan including several objects's renovation and restoration and to provide it to RA Government for governmental funding | Charentsavan municipality | RA Governement |  | n/a | 0 | 0 |  | A2.1.3 | Planned
O2.2 | Action (output) | Local and regional policies are in place, adopted and disseminated to ensure policy level protection and preservation of the heritage | Foundation of cultural development of Charentsavan, Municipality of Charentsavan | the Agency for the protection of Monuments of History and Culture Protection of the RA Ministry of Education, Science, Culture and Sports |  |  | 600 | 0
A2.2.1 | Activity | To update and develop Charentsavan city cultural objects and ICH assets preservation policy for monuments and assets of local cultural importance | Municipality of Charentsavan | n/a |  | n/a | 0 | 0 |  | A2.1.4 | Planned
A2.2.2 | Activity | To organize 2-day informative meetings for local policy makers and responsibles from the Agency for the protection of Monuments of History and Culture Protection of the RA Ministry of Education, Science, Culture and Sports, on syncronizing the actions and joint efforts | Municipality of Charentsavan | the Agency for the protection of Monuments of History and Culture Protection of the RA Ministry of Education, Science, Culture and Sports |  | n/a | 600 | 0 |  | A2.2.2 | Planned
A2.2.3 | Activity | To syncronize the actions with National cultural heritage protection policy on ongling basis, collaboration and information sharing | Municipality of Charentsavan | the Agency for the protection of Monuments of History and Culture Protection of the RA Ministry of Education, Science, Culture and Sports |  | n/a | 0 | 0 |  | A2.2.2 | Planned
O2.3 | Action (output) | Exhibition and proper communication of the cultural assets and intangible cultural heritage are carried out through different platforms /on site and virtually/ | Foundation of cultural development of Charentsavan, Municipality of Charentsavan | companies outsourced |  |  | 168500 | 0
A2.3.1 | Activity | To choose the place/ existing building for the Charentsavan cultural heritage museum and artspace within the city to become a beloved and convenient place for locals and visitors | Foundation of cultural development of Charentsavan, Municipality of Charentsavan | n/a |  | n/a | 0 | 0 |  |  | Planned
A2.3.2 | Activity | To develop the TOR for Charentsavan heritage museum/artspace architectural design and pro forma document | Foundation of cultural development of Charentsavan | n/a |  | n/a | 0 | 0 |  | A2.3.1 | Planned
A2.3.3 | Activity | To announce the tender, selection of architectural design | Foundation of cultural development of Charentsavan | n/a |  | n/a | 10000 | 0 |  | A2.3.1 | Planned
A2.3.4 | Activity | To select the developer/construction company and to implement the construction | Foundation of cultural development of Charentsavan | n/a |  | n/a | 120000 | 0 |  | A2.3.1 | Planned
A2.3.5 | Activity | To hire museum curator for development of concept and art vision of permanent exhibition | Foundation of cultural development of Charentsavan | n/a |  | n/a | 3500 | 0 |  | A2.3.1 | Planned
A2.3.6 | Activity | To hire design company to implement space develoment and furnishing of the museum/artspace | Foundation of cultural development of Charentsavan | n/a |  | n/a | 29000 | 0 |  | A2.3.1 | Planned
A2.3.7 | Activity | To implement workforce planning and hiring | Foundation of cultural development of Charentsavan | n/a |  | n/a | 0 | 0 |  | A2.3.1 | Planned
A2.3.8 | Activity | To manage the museum staff, organize its works, the contracts, payment system from local community budget and building maintenance costs | Foundation of cultural development of Charentsavan | n/a |  | n/a | 0 | 0 |  | A2.3.1, A2.3.7 | Planned
A2.3.9 | Activity | To collect artifacts for exhibiting in the museum from all over Armenia to demonstrate | Foundation of cultural development of Charentsavan | local inhabitants nd organizations |  | n/a | 1000 | 0 |  | A2.3.1 | Planned
A2.3.10 | Activity | To order preparation of digitalized materials and tools for digital represnetation of the materials in the museums | Foundation of cultural development of Charentsavan | companies outsourced |  | n/a | 5000 | 0 |  | A2.3.1 | Planned
A2.3.11 | Activity | To settle the rules of operation of the museum and the artspace, its contingency and sustainability plans | Foundation of cultural development of Charentsavan, Municipality of Charentsavan | local CCI artists |  | n/a | 0 | 0 |  | A2.3.1, A2.3.8 | Planned
O3 | Operative Goal (outcome) | Spatial development, communication of a strong brand and celebration of cultural heritage is a constant source of inspiration for economic and cultural entrepreneurs | Foundation of cultural development of Charentsavan, Municipality of Charentsavan | companies outsourced |  |  | 11400 | 0
O3.1 | Action (output) | Charentsavan branding is implemented and communicated ensuring emotional affiliations of the locals and strong linkages between the past and the future | Foundation of cultural development of Charentsavan | Companies outsourced |  |  | 8000 | 0
A3.1.1 | Activity | To prepare TOR to create Charentsavan brand identity, concept, visuals etc | Foundation of cultural development of Charentsavan | n/a |  | n/a | 0 | 0 |  |  | Planned
A3.1.2 | Activity | To announce, choose and handle the brand identity winner package | Foundation of cultural development of Charentsavan | n/a |  | n/a | 5000 | 0 |  | A3.1.1 | Planned
A3.1.3 | Activity | To order design and printing of visuals and materials to disseminate the brand in the city and beyond | Foundation of cultural development of Charentsavan | Companies outsourced |  | n/a | 3000 | 0 |  | A3.1.1 | Planned
O3.2 | Action (output) | Charentsavan master plan is developed to contribute to territorial development of the area | Municipality of Charentsavan |  |  |  | 0 | 0
A3.2.1 | Activity | To follow the results of the national tender of creation on Charentsavan master plan | Municipality of Charentsavan | Marz administration, RA Government |  | n/a | 0 | 0 |  |  | Planned
A3.2.2 | Activity | To organize discussions with local businesses and investors on implementation of master plan for developmental purposes of the area | Municipality of Charentsavan | Local businesses and investors |  | n/a | 0 | 0 |  |  | Planned
A3.2.3 | Activity | To properly distribute the master plan in Charentsavan webpage | Municipality of Charentsavan | n/a |  | n/a | 0 | 0 |  |  | Planned
O3.3 | Action (output) | Spatial development in all settlements is in the action plans and projects of local institutions, governmental organizations and local people | Municipality of Charentsavan | partner organizations |  |  | 0 | 0
A3.3.1 | Activity | Creation of small "local museums" and information corners in all settlements | Foundation of cultural development of Charentsavan | local organizations/local CSOs,governmenta organizations, schools local creative artists etc/ |  | n/a | 0 | 0 |  | A2.1.3 | Planned
A3.3.2 | Activity | To attract new and renown projects, artists to organize works for spatial development of the area based on cultural heritage and brand identity/ for instance, street art painters etc./ | Foundation of cultural development of Charentsavan | individuals and organizations |  | n/a | 0 | 0 |  | A2.1.3 | Planned
O3.4 | Action (output) | Charentsavan cultural heritage celebrations are organized and have huge interest among locals, tourists and visitors all over Armenia | Municipality of Charentsavan, Foundation of cultural development of Charentsavan | n/a |  |  | 3400 | 0
A3.4.1 | Activity | In-dept research results are disseminated via Charentsavan official pages to increase visibility of the objects | Municipality of Charentsavan, Foundation of cultural development of Charentsavan | n/a |  | n/a | 0 | 0 |  | A2.1.3 | Planned
A3.4.2 | Activity | To organize creative presentation of the photo album of Charentsavan culural heritage monuments prepared and printed during the project | Municipality of Charentsavan | local organizations and individuals |  | n/a | 500 | 0 |  |  | Planned
A3.4.3 | Activity | To organize knowledge sharing and cultural heritage presentation public events/3 events/ for local people from all settlements to generate shared knowledge and love to their cultural heritage | Municipality of Charentsavan, Foundation of cultural development of Charentsavan | local organizations and individuals |  | n/a | 900 | 0 |  |  | Planned
A3.4.4 | Activity | To organize the celebration of Charentsavan establishment day /on the actual day of 23th of April/ for the public | Municipality of Charentsavan, Foundation of cultural development of Charentsavan | local organizations and individuals |  | n/a | 2000 | 0 |  | A2.1.3 | Planned
A3.4.5 | Activity | To help and organize united plan of Chrentsavan heritage celebration in all public and governmental organizations of the area | Municipality of Charentsavan, Foundation of cultural development of Charentsavan | local organizations and individuals |  | n/a | 0 | 0 |  |  | Planned
A3.4.6 | Activity | To organize proper PR campaings for all the major events to attract visitors to the community | Municipality of Charentsavan, Foundation of cultural development of Charentsavan | n/a |  | n/a | 0 | 0 |  |  | Planned
O3.5 | Action (output) | Charentsavan entrepreneurs and private businesses are inspired by cultural life and heritage, as well as by the brand, and reflect it in their production/service provision | Municipality of Charentsavan, Foundation of cultural development of Charentsavan | Local businesses and investors |  |  | 0 | 0
A3.5.1 | Activity | To organize information sessions for local SMEs and factory owners on all the aspcets of cultural heritage preservation and their commercialization | Municipality of Charentsavan, Foundation of cultural development of Charentsavan | Local businesses and investors |  | n/a | 0 | 0 |  | A2.1.3 | Planned
A3.5.2 | Activity | Organize information sessions and intellectual property rights trainings for proper usage of the heritage asstes and keeping intellectual property | Municipality of Charentsavan, Foundation of cultural development of Charentsavan | Local businesses and investors |  | n/a | 0 | 0 |  |  | Planned
O4 | Operative Goal (outcome) | Charentsavan local CCI actors are empowered, their creative and entrepreneurial potential is unlocked for more inclusive and sustainable economic growth | Foundation of cultural development of Charentsavan |  |  |  | 38500 | 0
O4.1 | Action (output) | Capacity building of active local CCI entrepreneurs and policy and decision makers are implemented | Foundation of cultural development of Charentsavan |  |  |  | 15000 | 0
A4.1.1 | Activity | To prepare TOR to organize 5 week-long creative business incubator for CCIs and individuals from the area | Foundation of cultural development of Charentsavan |  |  | n/a | 0 | 0 |  |  | Planned
A4.1.2 | Activity | To announce, select and contract the winning company to conduct the creative incubator | Foundation of cultural development of Charentsavan | companies outsourced |  | n/a | 15000 | 0 |  |  | Planned
A4.1.3 | Activity | To implement the creative incubator for around 40 artists and creative entrepreneurs from the area with aim to develop their entrerpeneural skills | Foundation of cultural development of Charentsavan | companies outsourced, local artists and organizations |  | n/a | 0 | 0 |  |  | Planned
O4.2 | Action (output) | Art residencies, visit to creative cities, international exhibitions and hosted events put Charentsavan on the map of creative cities | Foundation of cultural development of Charentsavan | local and international cultural organizations |  |  | 0 | 0
A4.2.1 | Activity | To connect and get involved into the Council of Europe's Cultural routes project | Foundation of cultural development of Charentsavan | Ministry of Ecucation, Culture, Science and Sports of RA |  | n/a | 0 | 0 |  |  | Planned
A4.2.2 | Activity | Explore and organize a visit for local CCI artists to one cultural and industrial city in Eastern Europe to explore post-soviet | Foundation of cultural development of Charentsavan | marz administration and Ministry of Ecucation, Culture, Science and Sports of RA |  | n/a | 0 | 0 |  |  | Planned
A4.2.3 | Activity | To explore other mechanisms and opportunities for local CCIs to cooperate with artists from abroad and organize their exhibitions and sales | Foundation of cultural development of Charentsavan | n/a |  | n/a | 0 | 0 |  |  | Planned
O4.3 | Action (output) | Grant scheme implementation ensured local creative artists leveraged their production to new level and some new enterprises appeared | Foundation of cultural development of Charentsavan |  |  |  | 23500 | 0
A4.3.1 | Activity | To develop grant provision scheme and a plan for local CCI artists and entrerpeneurs to provide them small grants/ up to 10 winners/ to develop their business and to access the market | Foundation of cultural development of Charentsavan | local organizations and Municipality of Charentsavan |  | n/a | 20000 | 0 |  |  | Planned
A4.3.2 | Activity | To properly announce and collect applications for the competition | Foundation of cultural development of Charentsavan | local organizations and Municipality of Charentsavan |  | n/a | 0 | 0 |  |  | Planned
A4.3.3 | Activity | Organize selection committee and several meetings for public with participation of the committee members to promote and advice on the competition | Foundation of cultural development of Charentsavan | local organizations and Municipality of Charentsavan, individual experts all over Armenia |  | n/a | 0 | 0 |  |  | Planned
A4.3.4 | Activity | To organize pitching day to select the 20 winners of the grants | Foundation of cultural development of Charentsavan | local organizations and Municipality of Charentsavan |  | n/a | 500 | 0 |  |  | Planned
A4.3.5 | Activity | To oversee the grant provision to local artists and implementation of their busness plans accordingly | Foundation of cultural development of Charentsavan | local organizations and Municipality of Charentsavan |  | n/a | 0 | 0 |  |  | Planned
A4.3.6 | Activity | To organize stakeholder coordination and management actions through informal local active groups in each settlement/ 8 to be established in total, 1 in each and 2 in Charentsavan/ to promote cooperation and generation of ideas, organization of events and dissemination of imformation/ | Foundation of cultural development of Charentsavan | local organizations and Municipality of Charentsavan |  | n/a | 0 | 0 |  |  | Planned
A4.3.7 | Activity | To conduct end of project evaluation via hiring a company | Foundation of cultural development of Charentsavan |  |  | n/a | 3000 | 0 |  |  | Planned
1. Cathegory |  |  |  | Please use a logical framework as a guide and insert the activities/achievements/goals from there
2. Description |  |  |  | Please provide short description of the activity
3. Responsible entity |  |  |  | Please indicate which entity is responsible for the activity. Main applicant, co-applicant or maybe together? Or maybe there is an external company responsible for this activity?
4. Partners |  |  |  | Please indicate the partner (if any) who supports you in this activity or with whom you have planned this activity (This can be for example Ministry of Culture, local tourism office, local musical school etc.)
5. Timeframe |  |  |  | Please provide the exact time frame in which this activity is planned. E.g. October 2022-May 2023
6. Human resources needed |  |  |  | Please indicate who you need for the activity to be carried out (e.g. financial manager, local coordinator, photographer, etc.)
7. Planned costs |  |  |  | Please indicate the costs foreseen for this activity. You can take this part from the budget
8. Real costs |  |  |  | Not applicable for now. Needed when starting implementation
9. Assumptions |  |  |  | Please indicate any fact, that might be considered as a risk for impementing this activity
10. Links with other actions |  |  |  | Please list any other activities (if any) that may be related to this activity
11. Status |  |  |  | Please indicate the status of this activity. For this you can use the drop down menu. Initially, all activities will be indicated as "planned" unless otherwise is planned

## Timetable_Chart
Indicative action plan for implementing the action
2022-2023-2024 Years | (8/22) | (9/22) | (10/22) | (11/22) | (12/22) | (1/23) | (2/23) | (3/23) | (4/23) | (5/23) | (6/23) | (7/23) | (8/23) | (9/23) | (10/23) | (11/23) | (12/23) | (1/24) | (2/24) | (3/24) | (4/24) | (5/24) | (6/24) | (7/24) | (8/24) | (9/24) | (10/24) | (11/24) | (12/24)
Name of the activity | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29
Activity 1.1.1 To develop the draft charter of future foundation
Preparation of activity 1.1.1 | bar: M1
Implementation of activity 1.1.1 | bar: M1
Activity 1.1.2 To discuss the charter with stakeholders to decide the participation of each of them as founders
Preparation of activity 1.1.2 | bar: M2
Implementation of activity 1.1.12 | bar: M2
Activity 1.1.3 Registration of the foundation is implemented
Preparation of activity 1.1.3 | bar: M2
Implementation of activity 1.1.3 | bar: M2
Activity 1.1.4 To organize the hiring process of the manager of the Foundation and to decide on organizational chart
Preparation of activity 1.1.4 | bar: M2
Implementation of activity 1.1.4 | bar: M2
Activity 1.1.5 To organize a proper office space for the foundation
Preparation of activity 1.1.5 | bar: M2
Implementation of activity 1.1.5 | bar: M2
Activity 1.1.6 To procure equipment and office furniture for the staff of the foundation/for 3 people/
Preparation of activity 1.1.6 | bar: M2
Implementation of activity 1.1.6 | bar: M2
Activity 1.1.7 To outsource baseline assessment
Preparation of activity 1.1.7 | bar: M2
Implementation of activity 1.1.7 | bar: M2 to M3
Activity 1.2.1 Adoption of the current CDS into an action plan by the Foundation
Preparation of activity 1.2.1 | bar: M3
Implementation of activity 1.2.1 | bar: M3
Activity 1.2.2 To organize marz-level and national stakeholders meeting to inform and disseminate strategy and action plan
Preparation of activity 1.2.2 | bar: M4
Implementation of activity 1.2.2 | bar: M4
Activity 1.2.3 To implement available projects and opportunities mapping for the available cultural interchange and development actions by other national or international organizations that are in line with the CDS
Preparation of activity 1.2.3 | bar: M4 to M28
Implementation of activity 1.2.3
Activity 1.2.4 The Foundation is implementing the CDS and its action plan
Preparation of activity 1.2.4 | bar: M4 to M28
Implementation of activity 1.2.4 | bar: M4 to M28
Activity 1.2.5 The Foundation provides reports and organizes meetings to inform and present the operations
Preparation of activity 1.2.5 | bar: M5; M8; M11; M14; M17; M20; M23; M26 to M28
Implementation of activity 1.2.5 | bar: M5; M8; M11; M14; M17; M20; M23; M26 to M28
Activity 2.1.1 To make a list of intangible cultural heritage objects and collect preliminary data
Preparation of activity 2.1.1 | bar: M4
Implementation of activity 2.1.1 | bar: M4
Activity 2.1.2 To enhance the list and description of around 60 cultural heritage objects in the area
Preparation of activity 2.1.2 | bar: M4
Implementation of activity 2.1.2 | bar: M4
Activity 2.1.3 To conduct a research of cultural heritage objects, their current condition, location and mapping , provide conclusions for reconstruction/restoration needs and to collect stories of the most important artifacts to be included on the main exhibition of the future museum
Preparation of activity 2.1.3 | bar: M5
Implementation of activity 2.1.3 | bar: M5 to M8
Activity 2.1.4 In-dept research results are shared with stakeholders/ locally and nationally/ to engage into action
Preparation of activity 2.1.4 | bar: M8
Implementation of activity 2.1.4 | bar: M8
Activity 2.1.5 To develop 3-year cultural development plan of Charentsavan including several objects's renovation and restoration and to provide it to RA Government for governmental funding
Preparation of activity 2.1.5 | bar: M8 to M9
Implementation of activity 2.1.5 | bar: M8 to M9
Activity 2.2.1 To update and develop Charentsavan city cultural objects and ICH assets preservation policy for monuments and assets of local cultural importance
Preparation of activity 2.2.1 | bar: M8 to M9
Implementation of activity 2.2.1 | bar: M8 to M9
Activity 2.2.2 To organize 2-day informative meetings for local policy makers and responsibles from the Agency for the protection of Monuments of History and Culture Protection of the RA Ministry of Education, Science, Culture and Sports, on syncronizing the actions and joint efforts
Preparation of activity 2.2.2 | bar: M9
Implementation of activity 2.2.2 | bar: M9
Activity 2.2.3 To syncronize the actions with National cultural heritage protection policy on ongling basis, collaboration and information sharing
Preparation of activity 2.2.3 | bar: M9 to M27
Implementation of activity 2.2.3 | bar: M9 to M27
Activity 2.3.1 To choose the place/ existing building for the Charentsavan cultural heritage museum and artspace within the city to become a beloved and convenient place for locals and visitors
Preparation of activity 2.3.1 | bar: M9
Implementation of activity 2.3.1 | bar: M9
Activity 2.3.2 To develop the TOR for Charentsavan heritage museum/artspace architectural design and pro forma document
Preparation of activity 2.3.2 | bar: M8
Implementation of activity 2.3.2 | bar: M8
Activity 2.3.3 To announce the tender, selection of architectural design
Preparation of activity 2.3.3 | bar: M9
Implementation of activity 2.3.3 | bar: M9 to M11
Activity 2.3.4 To select the developer/construction company and to implement the construction
Preparation of activity 2.3.4 | bar: M11
Implementation of activity 2.3.4 | bar: M11 to M16
Activity 2.3.5 To hire museum curator for development of concept and art vision of permanent exhibition
Preparation of activity 2.3.5 | bar: M11
Implementation of activity 2.3.5 | bar: M11 to M12
Activity 2.3.6 To hire design company to implement space develoment and furnishing of the museum/artspace
Preparation of activity 2.3.6 | bar: M11 to M12
Implementation of activity 2.3.6 | bar: M11 to M12; M17 to M18
Activity 2.3.7 To implement workforce planning and hiring
Preparation of activity 2.3.7 | bar: M11 to M13; M19
Implementation of activity 2.3.7 | bar: M19
Activity 2.3.8 To manage the museum staff, organize its works, the contracts, payment system from local community budget and building maintenance costs
Preparation of activity 2.3.8 | bar: M13 to M20
Implementation of activity 2.3.8 | bar: M13 to M28
Activity 2.3.9 To collect artifacts for exhibiting in the museum from all over Armenia to demonstrate
Preparation of activity 2.3.9 | bar: M11 to M13
Implementation of activity 2.3.9 | bar: M11 to M13
Activity 2.3.10 To order preparation of digitalized materials and tools for digital represnetation of the materials in the museums
Preparation of activity 2.3.10 | bar: M13 to M15
Implementation of activity 2.3.10 | bar: M13 to M15
Activity 2.3.11 To settle the rules of operation of the museum and the artspace, its contingency and sustainability plans
Preparation of activity 2.3.11 | bar: M13 to M16
Implementation of activity 2.3.11 | bar: M13 to M16
Activity 3․1․1 To prepare TOR to create Charentsavan brand identity, concept, visuals etc
Preparation of activity 3․1․1
Implementation of activity 3․1․1
Activity 3․1․2 To announce, choose and handle the brand identity winner package
Preparation of activity 3․1․1
Implementation of activity 3․1․1
Activity 3․1․3 To order design and printing of visuals and materials to disseminate the brand in the city and beyond
Preparation of activity 3․1․1
Implementation of activity 3․1․1

## Sheet4 (hidden)
Ongoing
Planned
finished
stopped